## Sheet1
purpose: | To test the main functions of the ppit project
Requirement ID | sprint | Test Case Ref | Test Case Name | Description | Parameter | Checks | Expected Result | Actual Result | Pass/Fail | #bugs | comment | possible solution
1 | 1 | TC.001 | Login | to login as an admin and use the profiler | 1.run profiler 2.login as admin | admin can login and non admin personal cannot | the admin is able to log in | Does what was expected | pass
2 | 1 | TC.002 | Monitor Mode | monitor mode converts any faces captured by the webcam into binary code. This binary code is compared with others stored in the project folders. If the face captured is a match to the any image found in the folder, the person has been correctly identified. | 1.run profiler 2.login as admin 3.click the monitor mode button 4. stand in clear view of the camera | To determine if the face captured matches any person found in the database | Monitor mode can correctly identfy users using the webcam | Does what was expected | fail
3 | 1 | TC.003 | Profile Mode | profile mode converts any image provided to the user. This binary code is compared with others stored in the project folders. If the image provided is a match to the any image found in the folder, the person has been correctly identified. | 1.run profiler 2.login as admin 3.run profile mode 4.provide a picture to examine | To determine if the photo provide matches any person found in the database | Profile mode is able to identify users based on photos | Does what was expected | pass
4 | 1 | TC.004 | Attendance | Similar to monitor mode, but the faces captured are recorded to a file as part of an attendance | 1.run profiler 2.login as admin 3.click the monitor mode button 4. stand in clear view of the camera | To determine if the face captured matches any person found in the database and the attendance is recorded correctly with the right time and date | uses the webcam to record the attendance of the user based on facial recognition | Does what was expected | pass
5 | 4 | TC.005 | Add new person | Adds a new person that can have his/her data pulled up if they're identified by the profiler | 1.run profiler 2.login as admin 3.go to "add new person option" 4.enter details of new person. | to determine if the person added to the database is found | adds new person to profiler database | Does what was expected | pass
6 | 4 | TC.006 | Delete Person | Deleting a person from the profiler can prevent them from being identified by the profiler | 1.run profiler 2.login as admin 3.use profile mode to identify person found on database 4.go to bank information 5.delete a column found in the bank section of the users profile | to determine if the person deleted from the database is gone | deletes person from profiler database | Does what was expected | pass
7 | 4 | TC.007 | View Data | View data such as assets, bank, education, medical history or criminal record of people stored on the profiler | 1.run profiler 2.login as admin 3.use profile mode to identify person found on database 4.go to bank information 5.delete a column found in the bank section of the users profile | data viewed is from the correct person | to determine if the information provided matches to the correct person on MySQL | Does what was expected | pass
8 | 2 | TC.008 | View Actitvity | view all the changes made by any admin such as adding data or deleting data | 1.run profiler 2.login as admin 3.click "view activity" | actions on the profiler are shown with the date and time | To determine all actions on the profiler are logged and can be viewed anytime | Does what was expected | pass
9 | 2 | TC.009 | Add criminal record | adds a criminal record to people in the database, but this can only be done by an admin who is also garda | 1.run profiler 2.login as admin 3.use profile mode to identify person found on database 4.go to the "add criminal record" section of the profiler. 5.add a crime to the person identified. 6. if this fails, repeat steps 2 to , but log in as a garda admin | adds a criminal record, but only as a guard admin as it can prevent people from being assigned as admin. | To determine if criminals can be prevented to being assigned as admin | Does what was expected | pass
10 | 4 | TC.010 | add data to person |  | 1.run profiler 2.login as admin | adds data to persons' record | To determine if new data can be added to a persons' record | Does what was expected | pass
11 | 3 | TC.011 | add new admin |  | 1.run profiler 2.login as admin 3.go to "view database" option, 4.click the "assign admin" button on any individual found on the table | admins logged in can assign the role of admin to other people in the profiler database | To determine if a new person can be assigned as admin | Does what was expected | pass
12 | 4 | TC.012 | remove admin |  | 1.run profiler 2.login as admin 3.go to "view database" option, 4.click the "remove as admin" button on any individual found on the table | admins logged in can unassign the role of admin from people in the profiler database | To determine if a current admin can be unassigned as admin | Does what was expected | pass
13 | 3 | TC.013 | prevent admin add |  | 1.run profiler 2.login as admin 3.go to "view database" option, 4.click the "assign admin" button on any individual that has a criminal record. | checks if criminals aren't assigned as admin | The person who was selected to be admin should not have been assigned due to his/her criminal record. | Does what was expected | pass
14 | 3 | TC.014 | logout |  | 1.run profiler 2.login as admin 3.logout | log off as admin and let another admin log in | the program should shut down and you should be at the login screen when you run the program again | Does what was expected | pass